## Project Timeline
PROJECT MILESTONE:
PROJECT DETAILS
DATE | MILESTONE | POSITION | BASELINE
2016-10-03 | Project Start | -13 | 1
2016-10-14 | Proposal Due | -15 | 1
2016-10-17 | Iter 1 | 5 | 1
2016-10-17 | Usermodule | -5 | 1
2016-10-17 | Patients | -7 | 1
2016-10-31 | Iter 2 | 5 | 1
2016-10-31 | Services Database | -10 | 1
2016-10-31 | Task | -7 | 1
2016-11-03 | Acceptance | -15 | 1
2016-11-14 | Iter 3 | 5 | 1
2016-11-14 | Invoices | -5 | 1
2016-11-28 | Iter 4 | 5 | 1
2016-11-28 | Email Notification | -10 | 1
2016-12-12 | Iter 5 | 5 | 1
2016-12-12 | SMS Notification | -5 | 1
2016-12-26 | Iter 6 | 5 | 1
2016-12-26 | Report | -10 | 1
2017-01-09 | Iter 7 | 5 | 1
2017-01-09 | Fields Customsation | -5 | 1
2017-01-23 | Iter 8 | 5 | 1
2017-01-23 | Currency Conversion | -10 | 1
2017-02-06 | Iter 9 | 5 | 1
2017-02-06 | Analysis | -5 | 1
2017-02-20 | Iter 10 | 5 | 1
2017-02-22 | Midterm | -15 | 1
2017-03-06 | Iter 11 | 5 | 1
2017-03-06 | Timeline | -5 | 1
2017-03-06 | Create additional modules/tabs | -10 | 1
2017-03-20 | Iter 12 | 5 | 1
2017-03-20 | Buffer | -8 | 1
2017-03-27 | Poster Submission | -5 | 1
2017-04-03 | Iter 13 | 5 | 1
2017-04-03 | Buffer | -8 | 1
2017-04-10 | Final Presentation | -15 | 1
2017-04-21 | Poster Day | -15 | 1
Project Timeline Tips:
The role of the Position values in the Project Details table is to prevent the Milestone labels from overlapping each other on the timeline. Use positive numbers to position labels above the timeline and negative numbers to position them below.
To add additional Milestones, either insert new rows within the table or start typing below the last table entry and the table will automatically expand to accommodate your newly added data.